## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Animesh Sawant
PROJECT NAME: | Edumate(centralised college portal)
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2023-09-23
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Edumate |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2023-09-12 | Flexibility in Adapting to Changing Requirements | designing | No | The college environment is dynamic, and requirements can change rapidly. | making it more dynamic | self | Solved
2 | 2023-09-15 | Choosing right enviroment | development | No | choosing accurate softwares and function,libraries less bugs | always have backup plansfor any software related issues | self | Solved
3 | 2023-09-18 | Scalability is a Priority | development | No | scalability is paramount as user numbers grow. Implementing a robust infrastructure and monitoring system allowed us to accommodate a larger user base without compromising performance. | making efforts to make it more scalable | self | Solved
4 | 2023-09-20 | Communication is Fundamental | development | No | Effective communication with all stakeholders, including students is vital. | circulating google forms for their suggestions | self | Solved
5 | 2023-09-21 | Accessibility is Non-Negotiable | development | No | Prioritizing accessibility from the beginning is essential. | Implementing small accessiblity features | self | Solved
6 | 2023-09-21 | Testing and Quality Assurance are Critical | Testing | No | Rigorous testing and quality assurance processes are essential to catch and address bugs, errors, and usability issues before they impact users | setting up testing phases | self | Solved